## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Solar Panel Installation at Master Gardener Idea Garden
Total Amount Requested from SSC: | 56400
Amount Requested as: | 56400 | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Complete F&S Design of PV System | 4-6 weeks |  | 2018-01-15
Solicit Bids For PV System from Vendors based on F&S Design | 4-6 weeks |  | 2018-03-01
Select PV Installation Vendor based on F&S and SSC approval | 4 weeks |  | 2018-04-01
Solicit Bids for Sign Frame from Vendor used by Arboretum | 4 weeks |  | 2018-05-01
Order Educational Sign Frame, Receive Sign Frame | 6 weeks |  | 2017-08-15
Installation of Educational Sign, beginning Sept 1 | 2 weeks |  | 2018-09-15
Installation of PV System, beginning Sept 1 | 6 weeks |  | 2018-10-15
Complete Graphic Design of Educational Sign Display | 8 weeks |  | 2019-01-15
Install Sign Display into Sign Frame | 1 week |  | 2019-02-01
Planning and Promoting Educational Event, beginning March 1, 2019 | 8 weeks |  | 2019-05-01
Educational Event | 1 day |  | Early May 2019, TBA
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Installation of 4'x3' Concrete Pad for Educational Sign | 1200 | 1 | 1200
0
0
0
0
0
0
0
0
0
|  | Subtotal | 1200
Publicity & Communication
Graphic Design of Educational Sign Display | 650 | 1 | 650
Printing/production of Educational Sign Display | 250 | 1 | 250
0
0
0
0
0
0
0
0
|  | Subtotal | 900
Personnel & Wages
Extension Staff (costs/wages covered by U of I Extension) |  |  | 0
Other Contractors (costs/wages included in other budget items) |  |  | 0
F&S Engineers (costs/wages included in other budget items) |  |  | 0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
4 kW Solar Power System |  |  | 20000
Lighting and Receptacles |  |  | 2000
Trenching and Running Conduit to Existing Power Source |  |  | 20000
Contingency for Engineering and Design of Project |  |  | 10000
0
0
0
0
0
0
|  | Subtotal | 52000
General Supplies & Other
Educational Sign Frame, 24"x36", same format as Arboretum signage | 1500 | 1 | 1500
Insulated Cabinet for Heated Storage Area | 800 | 1 | 800
0
0
0
0
0
0
0
0
|  | Subtotal | 2300
|  | TOTAL BUDGET | 56400
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
End of Application