## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Green Source Building Panels
Total Amount Requested from SSC: | 68955
Amount Requested as: | Grant | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Accumulate Sawdust to store | Ongoing |  | currently ongoing
Designate Sawdust storage area | 2wk |  | 2018-05-01
Purchase Hydraulic Hot Press | 8-12wk |  | 2018-07-31
Mill Lumber | Ongoing |  | currently ongoing
Prep materials for press | 2-4wk |  | 2018-05-01
Dry Materials | 10-15wk |  | 2018-08-01
Work with university on build projects | Ongoing |  | currently ongoing
Build sustainable housing for community | 2-3 years |  | 2021-05-15
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
JOOS HP 70 8'x4' hydraulic hot press | 41000 | 1 | 41000
Glue Lamination Adhesives Gallon | 35 | 85 | 2975
Adhesive Roller Applicators | 100 | 3 | 300
ecopoxy (soybean based epoxy adhesive) | 7000 | 1 | 7000
rubbermaid roughneck wheeled storage box | 150 | 1 | 150
tools (drills, mixing paddles, etc) | 1450 | 1 | 1450
0
0
0
0
|  | Subtotal | 52875
Publicity & Communication
To be funded through proceeds of materials |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Graduate Assistant (5hr x 32wk x $15/hr) | 2400 | 2 | 4800
Department Supervisor (2hr x 32wk x $20/hr) | 1280 | 1 | 1280
0
0
0
0
0
0
0
0
|  | Subtotal | 6080
Project Budget per F&S
Electrical outlet install & upgrades required | 10000 | 1 | 10000
0
0
0
0
0
0
0
0
0
|  | Subtotal | 10000
General Supplies & Other
Supplies as needed to be funded by material sales | 0 | 1 | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 68955
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
Currently, there is no other funding being requested. Once we have established the system proposed, the project will become self funded. Partnerships through the local communities and businesses will help fund growth and any future endeavors with SSC being the principal capital funder. The goal is to teach students the importance of sustainability and create housing opportunity for less privilaged in our community through donations, grants and self funded efforts.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
End of Application