## Sheet1
Step II Application
Please submit this completed application and supporting documentation to Sustainability-Committee@Illinois.edu. The Working Group Chairs will be in contact with you regarding any questions about the application. If you have any questions about the application process, please contact the SSC Program Advisor, Micah Kenfield, at kenfield@illinois.edu
GENERAL INFORMATION
Project Title: | Illinois Sustainable Food Project – Extrusion Expansion
Total Amount Requested from SSC: | 248000
Amount Requested as: | GRANT | (LOAN or GRANT)
SCOPE, SCHEDULE, AND BUDGET VERIFICATION
If the project required you to obtain information from Facilities & Services Planning Division, please include that here and attach any supporting documentation.
Scope & Schedule
What is the plan for project implementation? Describe the key steps of the project including the start date, target completion date, target date for submitting a final report, and any significant tasks or milestones in the table below. Please be as detailed as possible. Insert additional rows if necessary.
Task | Timeframe (# of weeks to completion) |  | Estimated Completion Date
Procure Equipment | 6 months |  | Jul. 2018
Install Equipment | 3 months |  | Oct. 2018
Training & Testing | 1 month |  | Nov. 2018
Recipe Development | 1 month |  | Dec. 2018
Begin full production and ongoing improvement |  |  | Jan. 2019
Budget
List all budget items for which funding is being requested under the appropriate category in the following table. Include cost and total amount for each item requested. Please be as detailed as possible. Insert additional rows if necessary.
Item | Cost Per Item | Quantity | Total Request
Equipment & Construction Costs
Food Grade Production Components & Install | 138000 | 1 | 138000
0
Coating & Tumbler Drum Components & Install | 110000 | 1 | 110000
0
0
0
0
0
0
0
|  | Subtotal | 248000
Publicity & Communication
Costs of Marketing project at UIUC Dining Service (Dining Halls) is covered |  |  | 0
covered by UIUC Dining Services. Other online marketing |  |  | 0
planned does not have associated costs. Planned tours |  |  | 0
and printed article distribution will be included with |  |  | 0
other activities already covered by FSHN. |  |  | 0
0
0
0
0
0
|  | Subtotal | 0
Personnel & Wages
Costs of student internships and other labor |  |  | 0
covered by Dining Services |  |  | 0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
Project Budget per F&S
N/A - All equipment to be installed in FSHN Pilot Plant, a |  |  | 0
plug and play facility. |  |  | 0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
General Supplies & Other
N/A |  |  | 0
0
0
0
0
0
0
0
0
0
|  | Subtotal | 0
|  | TOTAL BUDGET | 248000
ENVIRONMENTAL AND ECONOMIC IMPACTS
Please include any other sources of funding that have been obtained or applied for, and please attach any relevant letters of support.
The total extruder line cost is ~$3.5M, and is being built for research and teaching activities. The request to SSC for $248,000 is for the pieces necessary to allow for food grade production on the machine. The remaining $3.25M is being paid for in a combination of equipment donations, grants, and FSHN department dollars. A majority of these are already paid for and in place.
Please estimate the greenhouse gas impact this project will have, if applicable. Use the University of Illinois at Urbana-Champaign Energy Management website to determine the cost of energy on campus and the following chart to determine GHG emissions.
| Electricity: 1.672 CO2lb/kWh | Diesel: 22.2 CO2lb/gallon
| Steam: 244.9 CO2lb/klb | Gasoline: 19.4 CO2lb/gallon
Chilled Water: 144.6 CO2lb/mmbtu
It would be difficult to calculate an exact savings without having extensive knowledge of the current supplier's supply chains, but it is apparent the GHG savings from the reduction in gasoline use will be substantial. The products produced on campus will travel no more than 5 miles from farm to consumption, compared with hundreds or thousands of miles with the current suppliers.
End of Application