## Sheet1
The Barn in the American Imagination
Developing Innovative Strategies to Promote Sustainable Wood Use in Region
Research to Develop Prototype for Proof of Concept
(Material Acquisition, R+D, Digital Fabrication and Installation)
Tasks for Research and Development |  | Labor Estimate (days) | Est. Duration (days) | Est. Cost | Schedule | Responsible | Notes
Obtain Barn Pieces (Salvage Lumber and Other Hardware) |  | 1 | 1 |  | 2017 (Already Completed) | Stan | This is the cost for the wood, bringing the barn down, disassembly, and sorting the wood
Moving Materials: Labor |  | 1 | 1 |  | 2017 (Already Completed) | Stan/2 Assistants | Five men to load and unload the truck
Moving Materials: Flatbed trailer and truck |  | 1 | 1 |  | 2017(Already Completed) | Stan | Truck, driver, and help with loading
Wood Preparation |  | 8 | 60 | 800 | March - May (8 Saturdays) | Aaron/Stan/Lowell/Students | Sorting, removing extra nails, strengthening sections
Purchase Wood Scanning Equipment (Lidar Sensor) |  | 1 | 30 | 4800 | May | Aaron | Scanning large fallen trees from above to calculate cubic/ft of usable material
Purchase Drone (DJI Matrice 600 Pro + Specialized Mount for Lidar) |  | 1 | 30 | 6000 | May | Aaron
Computer |  | 1 | 14 | 2000 | April | Aaron | We currently have one machine in our digital fabrication shop, but do not have sufficient resources to readily permit student access
Screen and Assesories |  | 1 | 14 |  | April | Aaron | Will obtain from University Surplus
Software for Translating Point Clouds to Discrete Geometry and Converting to G-code and Robot Code |  | 1 | 14 | 1250 | April | Aaron | Currently possess most software, but licenses for Rhino and Robotmaster will need to be acquired.
Research Phase - Scanning Timber |  | 30 | 120 | 2880 | May-August | Aaron/Students | Student Employees $12.00 per hour x 240 hours x 1 Student
Research Phase - Digital Fabrication with CNC and Robotics |  | 45 | 180 | 8640 | May-October | Aaron/Students | Student Employees $12.00 per hour x 360 hours x 2 Students
Pedestal for Robotic Arm |  | 1 | 30 | 5200 | April | Aaron | We currently have CNC and Robotic Arm, but need to acquire base to sustain lumber when using robotic arm
Pavilion design |  | 20 | 80 | 3840 | Spring-Summer 2018 | Aaron + 2 Students | Student Employees $12.00 per hour x 160 hours x 2 Students
Design approval |  | 2 | 21 |  | Spring 2018 | Aaron/Facilities and Services | University agreements to proceed
Adquisition of Additional Materials |  | 2 | 7 | 5500 | May-September | Aaron/Stan/Gerry/Assistant | To complete the design: includes milled wood from Architecture. We will also try to find a sponsor.
Fabrication of Prototypes |  | 30 | 120 | 6360 | August-December | Aaron + 2 Students | Student Employees $12.00 per hour x 240 hours x 2 Students and also for tools and machine use in wood and metal shop
TOTAL RESEARCH AND DEVELOPMENT |  |  |  | 47270
Projected Activities in Spring 2019
The Barn Raising: Cultural and Educational Programming
Installation on Site (The Barn Raising)
Site designation |  | 2 | 2 |  | Spring 2018 | Aaron/Stan with Facilities and Services | The students will need to think about the site
Site inspection |  | 2 | 2 |  | Spring/Summer 2018 | Aaron with Students | Identification of underground lines and cables prior to digging
Wood and Component transport to site |  | 1 | 1 | 800 | Spring 2019 | Stan
Site Prep and Aid in Site Installation (Contractors) |  | 3 | 3 | 2500 | Spring 2019
Pavilion Installation (Students) |  | 4 | 14 | 1536 | Spring 2019 | Aaron/Stan/Students | Student Employees $12.00 per hour x 32 hours x 4 Students
Assistance with Construction and Installation (Contractors) |  | 2 | 14 | 1500 | Spring 2019 | Stan | Work complementary to students
Pavilion Finishes |  | 2 | 7 | 1000 | Spring 2019
TOTAL BARN RAISING (Installation on Site) |  |  |  | 7336
Educational Programming and Development of Informational Materials |  |  |  | Est. cost | Schedule | Resp. | Notes
History of Barns in Illinois | [5 empty] | Aaron/Stan/Students | NPR
Visit to Barns in Region |  |  |  | 225 |  | Aaron/Stan/Students | 12 Person Van and estimated fuel
Visit to Amish Community/Barn raising in IN |  |  |  | 250 |  | Aaron/Stan/Students | 12 Person Van and estimated fuel
History of this Barn (the Pell Family) | [5 empty] | Aaron/Stan/Students | Jorge Lucero
Farm animals | [5 empty] | Will Seek Assistance | Large Animal Veterinary Program or ACES
Wild birds and barns | [5 empty] | Will Seek Assistance | Local Birdwatchers?
Wild animals and barns | [5 empty] | Will Seek Assistance | Wild Animal Rescue
My Uncle Has a Barn: Barns in arts | [5 empty] | Will Seek Assistance | Media Studies
A Bit of Binder Twine: the Barn as repair shop | [5 empty] | Will Seek Assistance | Industrial Design
Signage for history, pavilion and animal habitats |  |  |  | 750 |  | Graphic Design / Industrustrial Design
Publicity | [6 empty] | UIUC website/ email / Local Channels - Radio / TV
Events
Community Launch |  |  |  | 750 |  | Aaron/Stan/Students | We would like to create several educational opportunities to engage the UIUC Community.
Promotional materials and activities
Harvest dinner (Shared Dishes)
Barn dance
Demonstration of Milling Process and Visits to Local Artisans |  |  |  | 250 |  | Aaron/Stan and Lowell
Barn wood workshop |  |  |  | 750 |  | Aaron/Stan/Gerry
squirrel feeders
bird houses
bat houses
Theatrical performance |  |  |  | 750 |  | Will Seek Assistance
TOTAL COMMUNITY OUTREACH |  |  |  | 3725
TOTAL FOR PROJECT |  |  |  | 58331